## Slide 1: Feral Friends Final Presentation
By: Mark Bikakis, Hunter Brock, and Tyler Woods

## Slide 2: Introduction: What is the Feral Friends project?
Mobile application targeting Android devices
Intended to bring users together to help colonies of feral cats
Displays locations of colonies on a map for users to see

## Slide 3: Overview
Final Requirements vs Initial Requirements
Final Timeline vs Initial Timeline
Results vs Initial Expectations
Project Process Review
Work to be Done

## Slide 4: Final Requirements vs Initial Requirements
Requirements are similar in both initial and final iterations
Differ in fine details
Requirements include:
  Posting markers to the map
  Viewing markers on the map
  Signing into the application
These requirements made up core functionality of the application

## Slide 5: Final Timeline vs Initial Timeline
Initial timeline had clear cut dates and included important deadlines
The group followed initial timeline up until spring break
Severe complications due to circumstances around COVID-19 pandemic deeply impacted final timeline
The group tried their best to continue to follow original timeline but faced major roadblocks in mid/late march

## Slide 6: Final Timeline vs Initial Timeline Continued
Initial Timeline: 1/31 - 2/14: First Sprint - Finish Planning/Documentation
2/11: Group Meeting
2/14 - 2/28: Second Sprint
3/03: Presentation 2
2/28 - 3/13: Third Sprint
3/13 - 3/27: Fourth Sprint
3/24 - 4/7: Individual Presentations
3/27 - 4/20: Preparation of Final Deliverables
4/21: Final Presentations
Final Timeline:
1/31 - 2/14: First Sprint - Finish Planning/Documentation
2/11: Group Meeting
2/14 - 2/28: Second Sprint
3/03: Presentation 2
2/28 - 3/13: Third Sprint
3/12 - 3/27: Complications due to COVID-19 pandemic
3/27 - 4/15: Fourth sprint and Individual Presentations
4/9 - 4/20: Continued Work on the Application and Preparation of Final Deliverables
4/21: Final Presentations

## Slide 7: Results vs Initial Expectations
Initial expectations were set very high
Quickly found out some expectations were impossible to meet
Continued striving to meet goals, even through major “roadblocks”
Met most of our initial expectations in final product
Would like to have added a little more polish

## Slide 8: Project Process Review
Followed Agile/SCRUM development methods
Executed four two week long sprints to develop the application
Met every Friday to discuss progress and problems
Communication and tracking applications helped group stay focused and up to date
Strong teamwork helped process go as smoothly as possible, given the situation that unfolded this semester

## Slide 9: Work To Be Done
Better testing, including more rigorous security and general testing
Implement a way for users to upload pictures
Implement a group chat system
Implement AI to recognize TNR’ed cats
Plenty of other ideas that the group would have liked to implement

## Slide 10: Conclusion
Group enjoyed coming up with app idea and ways to improve it
Gained valuable experience working with a variety of different tools
Overcame adversity to continue working on project
Greatly strengthen communication and teamwork skills